## To Do List
|  | Product Back Log |  |  |  | Next Week | 0 | Today Total | 52
[6 empty] | This Week | 52 | Today Completed | 51
[6 empty] | Tomorrow | 0
Sprint # | Description | Due Date | Coder | Status | 1899-12-31 | Today | 52
1 | Scrub Data | 2021-02-10 | Andy | Completed
1 | DDL | 2021-02-10 | Jill | Completed
1 | DML | 2021-02-10 | Jill | Completed | 1899-12-31
1 | SP_DeleteAirParticulateByID | 2021-02-10 | Andy | Completed
1 | SP_DeleteAnimalMarkerByID | 2021-02-10 | Andy | Completed
1 | SP_GetAirParticulateByID | 2021-02-10 | Taylor | Completed
1 | SP_GetAnimalMarkerByID | 2021-02-10 | Andy | Completed | 1899-12-31
1 | SP_GetAnimalMarkerBySpecies | 2021-02-10 | Andy | Completed
1 | SP_GetAllAnimals | 2021-02-10 | Allan | Completed
1 | SP_GetUniqueSpecies | 2021-02-10 | Andy | Completed
1 | SP_InsertAirParticulate | 2021-02-10 | Taylor | Completed | 1899-12-31
1 | SP_InsertAnimalMarker | 2021-02-10 | Andy | Completed
1 | SP_UpdateAirParticulateByID | 2021-02-10 | Taylor | Completed
1 | SP_UpdateAnimalMarkerByID | 2021-02-10 | Andy | Completed
1 | Select by nearest location | 2021-02-10 | Andy | Completed
1 | Update Documents, README etc. | 2021-02-10 | Jill | Completed
1 | Finalize promote package | 2021-02-10 | Jill | Completed
2 | AnimalSightings function in C# | 2021-03-03 | Andy | Completed
2 | Update DDL to include tbl_Sites | 2021-03-03 | Jill | Completed
2 | Update DML insert program to insert tbl_Sites, and update tbl_AnimalMarkers insert | 2021-03-03 | Taylor | Completed
2 | Create a SP called SP_GetAllSites. Links Animal Sightings | 2021-03-03 | Jill | Completed
2 | Update Marker SPs to include SiteFK | 2021-03-03 | Jill | Completed
2 | Get Site Markers on to map. Call SP_GetAllSites | 2021-03-03 | Taylor | Completed
2 | Create Site modals. Include information from FK for Animal Sightings and FK for emission sources. Call on SP_getAnimalMarkerBySite, uses join to display emission information. | 2021-03-03 | Andy | Completed
2 | C# HTML and JavaScript to create webpage | 2021-03-03 | Andy | Completed
2 | Markers: Read function, calls on sp_GetAllAnimals | 2021-03-03 | Allan | Completed
2 | Form on webpage which prompts for the information for SP_InsertAnimalMarker with button to lead to form | 2021-03-03 | Andy | Completed
2 | User can click on a marker and click on a button called update entry. Uses SP_UpdateAnimalMarkerByID to update animal sighting information. | 2021-03-03 | Allan | Completed
2 | Add FK calculations to SP_UpdateAnimalMarkerByID | 2021-03-03 | Jill | Completed
2 | Markers: Create function, calls on sp_InsertAnimalMarker | 2021-03-03 | Andy | Completed
2 | Markers: Update functions, calls on sp_UpdateAnimalMarkerByID | 2021-03-03 | Allan | Completed
2 | Markers: Delete Function, calls on DeleteAnimalMarkerByID | 2021-03-03 | Allan | Completed
2 | Have SP run from DML insert program | 2021-03-03 | Allan | Completed
2 | Update Documents, README etc. | 2021-03-03 | Andy | Completed
2 | Finalize promote package | 2021-03-03 | Andy | Completed
3 | Overlay (placed and scaled on map) | 2021-03-24 | Jill | Completed
3 | Overlay slider that alters the opacity of Overlay | 2021-03-24 | Taylor | Completed
3 | AirParticulates delete function in C# | 2021-03-24 | Allan | Completed
3 | Create InfoWindows for airparticulates sites and add the delete button. | 2021-03-24 | Allan | Completed
3 | Create heatmap using airparticulates data | 2021-03-24 | Jill | Completed
3 | Create function that inserts air particulate info into DB from ASPX layer | 2021-03-24 | Jill | Completed
3 | Create button to insert air particulates info | 2021-03-24 | Taylor | Completed
3 | Sychronize all checkboxes and buttons to display most amount of information and consolidate DML_insert solution with the Radagast_Website solution | 2021-03-24 | Allan | Completed
3 | Update Documents, README etc. | 2021-03-24 | Allan | Completed
3 | Finalize promote package | 2021-03-24 | Allan | Completed
4 | Polylines - Create on Business Logic Layer, CRUD on Presentation Layer | 2021-04-14 | Andy | Completed
4 | Filter polyline functionality (coresponds to the same genus drop down menu) | 2021-04-14 | Andy | Completed
4 | Stylize polylines | 2021-04-14 | Andy | Completed
4 | Bug crushing - console window | 2021-04-14 | Allan | Completed
4 | Update CSS | 2021-04-14 | Taylor | Completed
4 | Update Documents, README etc. | 2021-04-14 | Taylor | Completed
4 | Finalize promote package | 2021-04-14 | Taylor | Copleted
SPRINT 1 PROGRESS
SPRINT 2 PROGRESS
SPRINT 3 PROGRESS
SPRINT 4 PROGRESS