## ProductRoadmap
Create a Work Plan in this worksheet. The title of this worksheet is in cell C1. Information about how to use this worksheet, including instructions for screen readers is in the About worksheet. Continue navigating down column A for further instructions. |  | Radagast Product Roadmap
Phase headings are in cells C2, D2, E2, and F2. There is an arrow shape in each cell with the text "Phase 1", "Phase 2", "Phase 3", and "Phase 4" in them, in addition to cell text, which is hidden behind each shape. Each phase has corresponding activities and outcomes that are listed below each heading. |  |  | Phase 2 | Phase 3 | Phase 4
Titles for each phase are listed in this row from cells C3 through F3. Overwrite or delete the sample data to create your own titles. | Date | February 10th | March 3rd | March 24th | April 14th
Activities for each phase are listed in the table starting in cell C4. Column B contains the word Activity in hidden text. This helps you navigate the table with a screen reader. Some screen readers will read the text as you navigate to other rows so you don't get lost between tables in this worksheet. Sample text for each phase is in columns C4 through F4. Enter your own list of activies for each phase in the Activites table. A shape overlaps column B with the word "Activities" as a visual representation of what is contained in this table. Continue to cell A11 for the next instruction. |  | Create project foundation | Animal Sighting location markers from SQL to ASPX.net | Adding the Overlay and Heatmap | Adding the site Polylines
|  | Scrub data | Write presentation layer and business logic layer CRUD for Location Markers +50pts | Add Overlay to website. Read and Update in Presentation layer and business layer. +33pts | Create polyline functionality on Business Logic Layer which is closely linked with marker functionality +15pts
|  | SQL coding: DML, DDL and S-Procs +50pts |  | Heatmap based on air particulates data with Create, Read and Delete functions in Presentation and C# layers +30pts | CRUD functions for polylines on Presentation layer +35pts
Outcomes for each phase are listed in the table starting in cell C14. Column B contains the word Outcome in hidden text. This helps you navigate the table with a screen reader. Some screen readers will read the text as you navigate to other rows so you don't get lost between tables in this worksheet. Sample text for each phase is in columns C14 through F14. Enter your own list of outcomes for each phase in the Outcomes table. A shape overlaps column B with the word "Outcomes" as a visual representation of what is contained in this table. Continue to cell A19 for the next instruction. |  | Required pts = 40 | Required pts = 40 | Required pts = 40 | Required pts = 40
|  | Planned pts = 50 | Planned pts = 50 | Planned pts = 63 | Planned pts = 50
|  | Results = | Results = | Results = | Results =
|  | Total Points Required = 160 | Total Planned Points = 213
This row marks the end of the sample table "Outcomes." To add more Outcomes for any of the phases, simply add new rows above this one.
Sprint 1
Sprint 2
Sprint 3
Sprint 4
Features
GPS Metrics
Goal